## Activity Log - Lauren
Name: Lauren |  | Project Group (Number): 2
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity (in mins) | Team Members Involved | Completed? | Notes:
1 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Person 1, Person 2 | Yes | Still to do: task X, task Y
1 | 2023-11-13 | GROUP MEETING: Created Miro board, SWOT analysis, brainstormed ideas on what we want our app to do and chucked some ideas on the Miro board and voted on what we liked. Discussed our personal strengths and weaknesses | 35 | Lauren, Louisa, Moira, Sheetal, Shiromini | Yes | Still to decide: Project App Idea
1 | 2023-11-14 | GROUP MEETING: Design brainstorming: Moscow analysis - Louisa ran exercise for what features we want in the app and we decided we’d come up with a name before the next meeting Decided on Project App Idea - Travel/Bucket List App | 30 | Lauren, Louisa, Moira, Sheetal, Shiromini | Yes | Still to decide: Name for the Project
2 | 2023-11-20 | GROUP MEETING: Moira created project repo and shared with group Added some tasks to the sprint board for people to take on Discussed if we’d do a python or JS based backend | 35 | Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Decide how we'd be implementing a back-end
3 | 2023-11-27 | GROUP MEETING: Discussed how HW2 fits into our project and filled in documentation for it Everyone shared what they had been working on and what they will be doing next | 40 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Start completing tasks and pushing to main repo
3 | 2023-11-28 | Created HTML and CSS for 'About us' page and entered my section | 30 | Lauren | Yes
4 | 2023-12-04 | Added an FAQ section to the 'About us' page | 20 | Lauren | Yes
4 | 2023-12-07 | GROUP MEETING: Everyone shares the tasks they've been working on and what they'll do next Agreed on doing the backend rather than cookies if we have the time, agreed we’d try and get all code finished by Tuesday 12th | 30 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Get all main code finished
4 | 2023-12-09 | Created a new seperate FAQ page and added styling | 60 | Lauren | Yes
4 | 2023-12-12 | Created a back end in order to have login functionality, but could not connect it successfully to the front end. Created a pull request in GitHub. | 120 | Lauren | No | Moira tried to make her own back-end instead
4 | 2023-12-12 | GROUP MEETING: Everyone shares the tasks they've been working on and what's left to do | 40 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Documentation / Clean up code; redux
4 | 2023-12-13 | Went through all meeting recordings and transcribed them, logged attendees and meeting time. Sent copy out to group for them to update their activity logs. | 140 | Lauren | Yes
|  | Total time (hours): | 9.6667
Total time:

## Activity Log - Louisa
Name: Louisa |  | Project Group (Number): 2
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity (in mins) | Team Members Involved | Completed? | Notes:
1 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Person 1, Person 2 | Yes | Still to do: task X, task Y
1 | 2023-11-13 | GROUP MEETING: Created Miro board, SWOT analysis, brainstormed ideas on what we want our app to do and chucked some ideas on the Miro board and voted on what we liked. Discussed our personal strengths and weaknesses | 35 | Lauren, Louisa, Moira, Sheetal, Shiromini | Yes | Still to decide: Project App Idea
1 | 2023-11-13 | Miro tasks - setting up sprint board, reference materials, project documentation | \a | Louisa | Yes
1 | 2023-11-14 | GROUP MEETING: Design brainstorming: Moscow analysis - Louisa ran exercise for what features we want in the app and we decided we’d come up with a name before the next meeting Decided on Project App Idea - Travel/Bucket List App | 30 | Lauren, Louisa, Moira, Sheetal, Shiromini | Yes | Still to decide: Name for the Project
1 | 2023-11-14 | GROUP MEETING: Ran through Moscow analysis features - what we must, should. could have etc Touched on design principles, accessibility etc (online compliance test is available for accessibility) Louisa to come up with user stories and product backlog so team can start assigning themselves tasks | 50 | Louisa, Moira, Sheetal, Shiromini | Yes | Still to do: Make a start on the app
3 | 2023-11-27 | GROUP MEETING: Discussed how HW2 fits into our project and filled in documentation for it Everyone shared what they had been working on and what they will be doing next | 40 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Start completing tasks and pushing to main repo
3 | 2023-11-30 | GROUP MEETING: Discussion over whether we are doing a login on not, (backend or cookies) Decided on using bootstrap with the HTML and CSS Everyone shares the tasks they'll be working on next and discuss ideas with the team for them | 40 | Louisa, Moira, Sheetal, Shiromini | Yes | Still to do: Decide if we want a login for the user and how we'll implement it
3 | 2023-11-30 | Created pack-list page with accordion, researched other elements like dropdowns and navigation techiniques | 120 | Louisa | Yes
3 | 2023-12-01 | Attempted back-end login using MySQL Workbench to build tables. Created node.js backend but issue with either Express Server or axios and failed to connect. Deleted branch. | 140 | Louisa | Yes | Passed SQL code to Lauren
3 | 2023-12-01 | Stood up initial pack-list page with items hard coded, work on page css, added emojis | 180 | Louisa | Yes
4 | 2023-12-06 | GROUP MEETING: Everyone shared the tasks they've been working on Discussed wether cookies or a backend would be better to use for Moira's Bucket List page and Louisa's Pack List page | 40 | Louisa, Moira, Sheetal | Yes | Still to do: Try to make a functional login page
4 | 2023-12-08 | Completed pack-list oncluding work on json list. Attempted to add in checkbox component but did not work due to formatting. Used Dall-E and Craiyon to generate AI images | 180 | Louisa | Yes
4 | 2023-12-07 | GROUP MEETING: Everyone shares the tasks they've been working on and what they'll do next Agreed on doing the backend rather than cookies if we have the time, agreed we’d try and get all code finished by Tuesday 12th | 30 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Get all main code finished
4 | 2023-12-09 | Stood up completed pack-list page | 170 | Louisa | Yes
5 | 2023-12-12 | GROUP MEETING: Everyone shares the tasks they've been working on and what's left to do | 40 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Documentation / Clean up code; redux
5 | 14/12//23 | Worked on responsiveness of pack-list on small screens.Re-wrote tests for pack-list as content was added to pages. Added own work to group doc and completed sections relating to Agile methodology | 150 | Louisa | Yes
5 | 2023-12-16 | Manual testing. Ensure code ready for recording | 30 | Louisa | No | Still to do: Complete Project Report
|  | Total time (hours): | 21.25

## Activity Log - Moira
Name: Moira |  | Project Group (Number): 2
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity (in mins) | Team Members Involved | Completed? | Notes:
1 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Person 1, Person 2 | Yes | Still to do: task X, task Y
1 | 2023-11-13 | GROUP MEETING: Created Miro board, SWOT analysis, brainstormed ideas on what we want our app to do and chucked some ideas on the Miro board and voted on what we liked. Discussed our personal strengths and weaknesses | 35 | Lauren, Louisa, Moira, Sheetal, Shiromini | Yes | Still to decide: Project App Idea
1 | 2023-11-14 | GROUP MEETING: Design brainstorming: Moscow analysis - Louisa ran exercise for what features we want in the app and we decided we’d come up with a name before the next meeting | 28 min | Lauren, Louisa, Moira, Sheetal, Shiromini | yes | Still to decide: Name for the Project
1 | 2023-12-14 | GROUP MEETING: Ran through Moscow analysis features - what we must, should. could have etc. Touched on design principles, accessibility etc. (online compliance test is available for accessibility)Louisa to come up with user stories and product backlog so team can start assigning themselves tasks | 51min | Louisa, Moira, Sheetal, Shiromini | yes | Still to do: Make a start on the app
2 | 2023-11-18 | Create a repo for the project and researching for an API to show Country,capital | 2 hours | Moira | no | Still search to do
2 | 2023-11-20 | GROUP MEETING: Moira created project repo and shared with group Added some tasks to the sprint board for people to take on Discussed if we’d do a python or JS based backend | 33min | Lauren, Moira, Sheetal, Shiromini | yes | Still to do: Decide how we'd be implementing a back-end
2 | 2023-11-23 | Start working on the api in my branch and explore the integration process with React | 3 hours | Moira | no | still work on to do
2 | 2023-11-24 | Keep building the API and create various components, including MapSearch and Map. | 4hours | Moira | no
3 | 2023-11-27 | GROUP MEETING: Discussion on how HW2 fits into our project and filled in documentation for it Everyone shared what they had been working on and what they will be doing next | 40min | Louisa, Lauren, Moira, Sheetal, Shiromini | yes | Still to do: Start completing tasks and pushing to main repo
3 | 2023-11-28 | Add the Map integration to the bucket list | 3 hours | Moira | yes | need to fix search country bar so when search again the previous will be hidden
3 | 2023-11-30 | GROUP MEETING: Discussion over whether we are doing a login on not, (backend or cookies) Decided on using bootstrap with the HTML and CSS Everyone shares the tasks they'll be working on next and discuss ideas with the team for them + looking to find hero image and start to build a bit of home | 39 min meet +2hours(my own) | Louisa, Moira, Sheetal, Shiromini | yes | still work to do on image and animation +Still to do: Decide if we want a login for the user and how we'll implement it
3 | 2023-12-01 | Working on the MapComponent and MapSearch and working in the css | 3hours | Moira | no | still need work to do css
3 | 2023-12-02 | Add more css on the Map and keep building Home Page | 2hours | Moira | no
4 | 2023-12-04 | update homepage with animation | 3 hours | Moira | maybe | need review from the team
4 | 2023-12-05 | update navbar-responsive burger menu in mobile view | 7hours | Moira | yes | need review from the team
4 | 2023-12-06 | Unite-testing search bar for country + GROUP MEETING: Everyone shares the tasks they've been working on Discuss wether cookies or a backend would be better to use for Moira's Bucket List page and Louisa's Pack List page | 4hours+39min meeting | Louisa, Moira, Sheetal | yes
4 | 2023-12-07 | Add a place to save a bucket list + GROUP MEETING: Everyone shares the tasks they've been working on and what they'll do next Agreed on doing the backend rather than cookies if we have the time | agreed we’d try and get all code finished by Tuesday 12th" | Louisa, Lauren, Moira, Sheetal, Shiromini | no yet and yes for the meeting | Still to do: Get all main code finished
4 | 2023-12-08 | implement the saved bucket list + start to write the report | 2 hours | Moira
4 | 2023-12-09 | fixed the bucket list and make it responsive | 3 hours | Moira | no yet | still work to do
4 | 2023-12-10 | fixed the map to be responsive | 6 hours | Moira |  | I think so
5 | 2023-12-11 | change colour of bg-list-item and fixed mediaquery | 2hours | Moira | yes
5 | 2023-12-12 | trying to implement the backend for the login + meeting | all day | Moira | no | so much to do
5 | 2023-12-13 | Set up signup but still problem with login and git + "GROUP MEETING: Everyone shares the tasks they've been working on and what's left to do " | all day + 40 min | Louisa, Lauren, Moira, Sheetal, Shiromini | no yet | Still to do: Documentation / Clean up code; redux
5 | 2023-12-14 | Resolve a problem with git merge + update report + updated Readme file | 4hours | Moira | no yet | need to finish login style
5 | 2023-12-15 | Updated report + add some style to the login | 4hours | Moira | no yet | need a bit update on report
5 | 2023-12-16 | Fixed some issues on testing |  | Moira | yes
Total time:

## Activity Log - Sheetal
Name: Sheetal |  | Project Group (Number): 2
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity (in mins) | Team Members Involved | Completed? | Notes:
1 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 mins | Person 1, Person 2 | Yes | Still to do: task X, task Y
1 | 2023-11-13 | GROUP MEETING: Created Miro board, SWOT analysis, brainstormed ideas on what we want our app to do and chucked some ideas on the Miro board and voted on what we liked. Discussed our personal strengths and weaknesses | 35 | Lauren, Louisa, Moira, Sheetal, Shiromini | Yes | Still to decide: Project App Idea
1 | 2023-11-14 | GROUP MEETING: Design brainstorming: Moscow analysis - Louisa ran exercise for what features we want in the app and we decided we’d come up with a name before the next meeting Decided on Project App Idea - Travel/Bucket List App | 30 | Lauren, Louisa, Moira, Sheetal, Shiromini | Yes | Still to decide: Name for the Project
1 | 2023-11-14 | GROUP MEETING: Ran through Moscow analysis features - what we must, should. could have etc Touched on design principles, accessibility etc (online compliance test is available for accessibility) Louisa to come up with user stories and product backlog so team can start assigning themselves tasks | 50 | Louisa, Moira, Sheetal, Shiromini | Yes | Still to do: Make a start on the app
2 | 2023-11-20 | GROUP MEETING: Moira created project repo and shared with group Added some tasks to the sprint board for people to take on Discussed if we’d do a python or JS based backend | 35 | Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Decide how we'd be implementing a back-end
2 | 2023-11-24 | Started basic wireframe on figma to share with the team, for us to build on at next meeting | 60 | Sheetal | Yes | Still to do: Decide on what pages we'll have and which components on each
2 | 2023-11-24 | Added Header Component with basic nav menu and basic styling to be built upon | 60 | Sheetal | Yes | Still to do: Decide on what pages we'll be doing for nav menu and logo needed; Footer component
2 | 2023-11-26 | Added Footer Component with basic text, social icons and basic styling to be built upon | 30 | Sheetal | Yes | Still to do: Decide on what pages we'll be doing for nav menu and logo needed
3 | 2023-11-27 | GROUP MEETING: Discussed how HW2 fits into our project and filled in documentation for it Everyone shared what they had been working on and what they will be doing next | 40 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Start completing tasks and pushing to main repo
3 | 2023-11-28 | Lauren started the about page for each team member to write up their profile - I input my section | 15 | Lauren, Sheetal | Yes | Still to do: Decide on what other components are needed for each page
3 | 2023-11-30 | GROUP MEETING: Discussion over whether we are doing a login on not, (backend or cookies) Decided on using bootstrap with the HTML and CSS Everyone shares the tasks they'll be working on next and discuss ideas with the team for them | 40 | Louisa, Moira, Sheetal, Shiromini | Yes | Still to do: Decide if we want a login for the user and how we'll implement it
3 | 2023-12-01 | Colour scheme for our web app decided; the footer icons needed to be changed so they were more visible with the new footer colour - changed footer icons | 15 | Sheetal | Yes | Still to do: Link the social icons in the footer to something
3 | 2023-12-01 | Started looking at how I could make a testimonial slider - found some options: React Slick which uses jQuery Slick library and React Bootstrap 5 Testimonial Slider, or I could build it from scratch | 60 | Sheetal | Yes | Still to do: Decide how I'll do the testimonial component
4 | 2023-12-04 | Decided to make the testimonial carousel using React Slick; customised the provided carousel to suit our design needs; made custom arrows in the colour wanted | 120 | Sheetal | Yes | Still to do: Adjust styling to match our colour scheme
4 | 2023-12-06 | Adjust styling of testimonial-carousel to match our brand, placed on homepage and pushed to main for review from team | 40 | Sheetal | Yes | Still to do: Wait for team review and make changes as necessary; testing on testimonial-carousel component
4 | 2023-12-06 | Did unit testing on the testimonial-carousel component. 1 test on the rendering of the carousel slider, 1 on the rendering of the text aove the slider and one test to check the click function works on the "back to top" button below the carousel | 120 | Sheetal | Yes | Still to do: Await feedback for changes
4 | 2023-12-06 | GROUP MEETING: Everyone shared the tasks they've been working on Discussed wether cookies or a backend would be better to use for Moira's Bucket List page and Louisa's Pack List page | 40 | Louisa, Moira, Sheetal | Yes | Still to do: Try to make a functional login page
4 | 2023-12-06 | After team review on testimonial-carousel component, decided to put it on the about page instead of home; moved component to about page | 20 | Sheetal | Yes | Still to do: adjust the component to match the rest of the about page
4 | 2023-12-07 | Updated styling on about page to be more cohesive with the homepage and testimonial component styling adjusted too | 60 | Sheetal | Yes | Still to do: possibly move the "back-to-top button" into it's own component so it can be used on other pages if wanted
4 | 2023-12-07 | Front-end for SignUp/Login Page with dummy login details | 120 | Sheetal | Yes | Still to do: possibly back-end so it works as a login
4 | 2023-12-07 | GROUP MEETING: Everyone shares the tasks they've been working on and what they'll do next Agreed on doing the backend rather than cookies if we have the time, agreed we’d try and get all code finished by Tuesday 12th | 30 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Get all main code finished
4 | 2023-12-09 | Linked Facebook and Instagram icons in footer to social media pages | 15 | Sheetal | Yes | Still to do: make a contact page to link email icon to
4 | 2023-12-09 | Added contact page and styled | 90 | Sheetal | Yes | Still to do: link email footer icon to contact page
4 | 2023-12-09 | Linked Email footer icon to Contact page | 10 | Sheetal | Yes
4 | 2023-12-09 | Connecting issues with FAQ page; call with Lauren to help resolve | 20 | Lauren, Sheetal | Yes
4 | 2023-12-12 | GROUP MEETING: Everyone shares the tasks they've been working on and what's left to do | 40 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Documentation / Clean up code; redux
5 | 2023-12-12 | Begin write up of Project Report as the team add in their points | 30 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Complete Project Report
5 | 2023-12-13 | Shiromini pushed her weather-forecast component and requested review; worked off Shiromini's branch to find a good place for weather-forecast component to make it fit in our app; pushed branches for review from the rest of the team | 20 | Shiromini, Sheetal | Yes | Still to do: styling for weather component
5 | 2023-12-14 | Continue write up of Project Report as the team add in their points | 60 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Complete Project Report
5 | 2023-12-16 | Final checks on code and completed Project Report | 60 | Sheetal | Yes
|  | Total time (hours): | 22.75

## Activity Log - Shiromini
Name: Shiromini |  | Project Group (Number): 2
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity (in mins) | Team Members Involved | Completed? | Notes:
1 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Person 1, Person 2 | Yes | Still to do: task X, task Y
1 | 2023-11-13 | GROUP MEETING: Created Miro board, SWOT analysis, brainstormed ideas on what we want our app to do and chucked some ideas on the Miro board and voted on what we liked. Discussed our personal strengths and weaknesses | 35 | Lauren, Louisa, Moira, Sheetal, Shiromini | Yes | Still to decide: Project App Idea
1 | 2023-11-14 | GROUP MEETING: Design brainstorming: Moscow analysis - Louisa ran exercise for what features we want in the app and we decided we’d come up with a name before the next meeting Decided on Project App Idea - Travel/Bucket List App | 30 | Lauren, Louisa, Moira, Sheetal, Shiromini | Yes | Still to decide: Name for the Project
1 | 2023-11-14 | GROUP MEETING: Ran through Moscow analysis features - what we must, should. could have etc Touched on design principles, accessibility etc (online compliance test is available for accessibility) Louisa to come up with user stories and product backlog so team can start assigning themselves tasks | 50 | Louisa, Moira, Sheetal, Shiromini | Yes | Still to do: Make a start on the app
2 | 2023-11-20 | GROUP MEETING: Moira created project repo and shared with group Added some tasks to the sprint board for people to take on Discussed if we’d do a python or JS based backend | 35 | Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Decide how we'd be implementing a back-end
3 | 2023-11-27 | GROUP MEETING: Discussed how HW2 fits into our project and filled in documentation for it Everyone shared what they had been working on and what they will be doing next | 40 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Start completing tasks and pushing to main repo
3 | 2023-11-30 | GROUP MEETING: Discussion over whether we are doing a login on not, (backend or cookies) Decided on using bootstrap with the HTML and CSS Everyone shares the tasks they'll be working on next and discuss ideas with the team for them | 40 | Louisa, Moira, Sheetal, Shiromini | Yes | Still to do: Decide if we want a login for the user and how we'll implement it
4 | 2023-12-07 | GROUP MEETING: Everyone shares the tasks they've been working on and what they'll do next Agreed on doing the backend rather than cookies if we have the time, agreed we’d try and get all code finished by Tuesday 12th | 30 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Get all main code finished
4 | 2023-12-10 | Start on location search. Find an api that would give coordinates and attempt at using. Watch tutorials. | 320 | Shiromini | No | Still to do: Implement the APIs
4 | 2023-12-11 | Implement location search | 105 | Shiromini | Yes | Still to do: Implement the weather API
| 2023-12-12 | Implement weather API | 120 | Shiromini | Yes | Still to do: styling for weather component
4 | 2023-12-12 | GROUP MEETING: Everyone shares the tasks they've been working on and what's left to do | 40 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Documentation / Clean up code; redux
5 | 2023-12-12 | Begin write up of Project Report as the team add in their points | 30 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Complete Project Report
5 | 2023-12-13 | Work on the component including adding to Louisa's packlist page | 240 | Shiromini | Yes | Still to do: styling for weather component
5 | 2023-12-13 | Shiromini pushed her weather-forecast component and requested review; worked off Shiromini's branch to find a good place for weather-forecast component to make it fit in our app; pushed branches for review from the rest of the team | 20 | Shiromini, Sheetal | Yes | Still to do: styling for weather component
5 | 2023-12-14 | Continue write up of Project Report as the team add in their points | 60 | Louisa, Lauren, Moira, Sheetal, Shiromini | Yes | Still to do: Complete Project Report
5 | 2023-12-14 | Work on css for my component | 135 | Shiromini | Yes | Still to do: project write up
5 | 2023-12-15 | Add today's date to the weather page, change background colour depending on temp and other little improvements. Resolve merge conflict. | 90 | Shiromini | Yes | Still to do: project write up
5 | 2023-12-15 | Write some bits to the project report | 45 | Shiromini | Yes
5 | 2023-12-15 | Notice that location search dropdown is not working. Check my code. Check commits etc. Learn how to go to previous version using Git. | 150 | Shiromini | No | Still to do: resolve crisis
5 | 2023-12-16 | Go through each branch to find which branch caused location search dropdown to not work. Then work out which file change and finally which line. Communicate in the Slack about my findings and fix with the team. | 70 | Shiromini | Yes | Still to do: activity log
5 | 2023-12-16 | Activity log | 60 | Shiromini | Yes
29.0833